## Rundown Upgrade
Activity Task |  | Impacted Service | Command | Expected Result | Rollback Task | Timeplan | Duration (mins) | Actual Start | Actual End | Status | Note | Mitigation Plan
Activity Task
Task A | Pre-requisite Activity |  |  |  | -
Task A1 | Open proactive case to F5 Support | No | - |  | - | [5 empty] | Done
Task A2 | Generate QKView | No | - | QKView uploaded to Ihealth | - | [5 empty] | Done
Task A3 | validate host configuration | No | #tmsh load sys config verify #tmsh show gtm iquery | no error indication | - | [5 empty] | Done
Task A5 | Generate UCS Backup and pull to local | No | - | UCS backup file exported to local | - | [5 empty] | Done
Task A6 | Upload TMOS ISO and cheksum | No | - | TMOS ISO uploaded to vCMP and checksum success | - | [5 empty] | Done
Task A7 | Service check date Appliance | No | check license check date: #cat /etc/version_date check service check date: #tmsh show sys license ¦ grep "Service Check Date" | Service check date is later than license check date | - | [5 empty] | Done BIG-IP 17.1.x License Check Date: 2023-02-08 | esbpclbltmd1:Active:Standalone] ~ # tmsh show sys license ¦ grep "Service Check Date" Service Check Date 2022/05/30
Task A8 | Collect VS Mapping data | No | - | Collect VS list and PIC | - | [5 empty] | Done
Task B | Activity Precheck | [5 empty] | 0.020833
Task B1 | 1.F5 utilization (24 hours & 7 days) 2.Network map (summary & detail) 3. VS statistics | No | - | 1.no error 2.big3d is running 3.network map status and VS statistics maintained | - | 0.89583 | 0.020833 | 0.39583 | 0.91667
Task C | Upgrade lb : esbpclbltmd1.telkomsel.co.id |  |  | esbpclbltmd1.telkomsel.co.id is upgraded to BIGIP-17.1.1.3 ENG |  |  | 0.083333
Task C1 | Reactivate License | No | #tmsh #show sys license ¦ grep -i 'service check date' System > License > Re-activate. Activation Method = Manual > Next. Download the dossier and connect to the F5 Product Licensing page at secure.f5.com. Click for Activate F5 product registration key. Upload the dossier > Next > Download License. Back to F5 box > upload license file > Next. #tmsh #show sys license ¦ grep -i 'service check date' | License Reactivated |  | 0.91667 | 0.020833 | 0.92153 | 0.92569
Task C2 | Install iso to boot volume HD1.2 | No | Access esbpclbltmd1.telkomsel.co.id via GUI or CLI: #tmsh #install sys software image BIGIP-17.1.1.3.iso volume HD1.2 | BIGIP-17.1.1.3.iso is installed on boot volume HD1.2 |  | 0.9375 | 0.020833 | 0.92569 | 0.94444
Task C3 | Install ENG iso to boot volume HD1.2 | No | Access esbpclbltmd1.telkomsel.co.id via GUI or CLI: #tmsh #install sys software hotfix Hotfix-BIGIP-17.1.1.3.0.12.5-ENG.iso volume HD1.2 | Hotfix-BIGIP-17.1.1.3.0.12.5-ENG.iso is installed on boot volume HD1.2 |  | 0.95833 | 0.020833 | 0.94444 | 0.95069
Task C4 | force offline standby box | No | #tmsh #run sys failover offline #save sys config | esbpclbltmd1.telkomsel.co.id status is offline |  | 0.97917 | 0.0034722 | 0.95208 | 0.95278
Task C5 | copy current configuration and switchboot to boot volume HD1.2 | No | #cpcfg --source=HD1.3 HD1.2 #switchboot -b HD1.2 #reboot | - current configuration is copied to boot volume HD1.2 - esbpclbltmd1.telkomsel.co.id is rebooted and using boot volume HD1.2 | Fallback C | 0.98264 | 0.020833 | 0.95278 | 0.97083 |  | 1. Configuration loaded successfully 2. License running 3. Version Upgraded Successfully
Task C6 | release forced offline standby box | No | Access esbpclbltmd1.telkomsel.co.id via CLI: #tmsh #run sys failover online #save sys config | esbpclbltmd1.telkomsel.co.id status is online |  | 0.0034722 | 0.0034722 | 0.97083 | 0.97292
Task C7 | verify F5 configuration and network map status | No | #tmsh load sys config verify #tmsh show gtm iquery | no error big3d is running network map status and VS statistics maintained |  | 0.010417 | 0.013889 | 0.97292 | 0.97917
Task D | Activity Postcheck | [5 empty] | 0.020833
Task D1 | F5 utilization (24 hours & 7 days) Network map (summary & detail) VS statistics | No | - | -no error -big3d is running -network map status and VS statistics maintained |  | 0.024306 | 0.020833 | 0.97917 | 0.98125
Fallback Plan
Fallback C | Switchboot Back to Existing TMOS 13.1.5 |  |  | Boot to Existing TMOS 13.1.5 |  |  | 0.020833
| copy current configuration and switchboot to boot volume HD1.3 | No | #switchboot -b HD1.3 #reboot | current configuration is copied to boot volume HD1.3 esbpclbltmd1.telkomsel.co.id is rebooted and using boot volume HD1.3 | - |  | 0.013889
| verify F5 configuration and network map status | No | #tmsh load sys config verify #tmsh show gtm iquery | no error big3d is running network map status and VS statistics maintained | - |  | 0.0069444

## Service&PIC List
name | VS | APP | Sum of clientside.curConns | Sum of clientside.maxConns | Apps DIVISION | APPS CUSTODY PIC | PIC Officer | PIC Staff
esbpclbltmd1.telkomsel.co.id | VS | OCP4 | 2547 | 52797 | ESB API Gateway and Data Cache Management Department | fatkur_rohman@telkomsel.co.id muhammad_m_abdullah@telkomsel.co.id | gradi_adriandi@telkomsel.co.id ahmad_e_irsad@telkomsel.co.id muhammad_rifqi@telkomsel.co.id | armansyah@telkomsel.co.id dwi_n_thiertian@telkomsel.co.id
| VS | Infra | 21 | 21217
| VS | APIGW | 0 | 18792
| VS | api | 0 | 9160
| VS | CIAMIGNFT | 0 | 4092
| VS | CIAMAMNFT | 0 | 2355
| VS | CIAMIDMNFT | 0 | 1086
| VS | Master | 10 | 265
| VS | Sigma | 2 | 62
| VS | OPE | 0 | 16
| VS | KUBE | 0 | 4
| VS | ESB | 0 | 2

## VS LIST
No. | hostname | Management IP | Virtual Server Name | VS IP:PORT | VS Status | VS State | Pool Name | Pool Member Name | Pool Member Status | Pool Member State | clientside.curConns | clientside.maxConns
| esbpclbltmd1 | 10.42.96.35 | POC_AS | /Common/10.42.98.96:5100 | offline | The children pool member(s) are down | AS_POC | 10.42.98.10:30621 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | POC_AS | /Common/10.42.98.96:5100 | offline | The children pool member(s) are down | AS_POC | 10.42.98.10:51621 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | POC_AS | /Common/10.42.98.96:5100 | offline | The children pool member(s) are down | AS_POC | 10.42.98.10:51622 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | POC_AS | /Common/10.42.98.96:5100 | offline | The children pool member(s) are down | AS_POC | ocprndapp1:443 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-ADMIN-MANAGER | /Common/10.42.98.99:8443 | available | The virtual server is available | PL_APIGW_KONG-ADMIN-MANAGER | 10.42.98.109:31021 | up | enabled | 0 | 52
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-ADMIN-MANAGER | /Common/10.42.98.99:8443 | available | The virtual server is available | PL_APIGW_KONG-ADMIN-MANAGER | 10.42.98.110:31021 | up | enabled | 0 | 52
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-ADMIN-MANAGER | /Common/10.42.98.99:8443 | available | The virtual server is available | PL_APIGW_KONG-ADMIN-MANAGER | 10.91.131.10:443 | up | enabled | 0 | 52
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.104:30148 | down | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.108:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.109:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.109:32671 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.110:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.110:32671 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.118:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.119:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.124:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.125:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.37:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.90:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | 10.91.131.69:443 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | _auto_10.91.130.27:443 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | _auto_10.91.133.250:443 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbactbwl2dapp2:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbactbwl3dapp1:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbactbwl3dapp2:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp10:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp1:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp2:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp3:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp4:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp8:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp9:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbmsgsl3dapp1:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbmsgsl3dapp2:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbmstcopdapp4:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | esbmstcopdapp5:30148 | down | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | internal-k8s-kong34dpsznprod-f17f692a4e-88119219.ap-southeast-3.elb.amazonaws.com:443 | fqdn-up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | ocprndapp1:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | ocprndapp3:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API | /Common/10.42.98.101:883 | available | The virtual server is available | PL_APIGW_KONG-API | ocprndapp4:30148 | up | enabled | 0 | 38644
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API-DIGIHUB | /Common/10.42.98.101:993 | available | The virtual server is available | PL_APIGW_KONG-API-DIGIHUB | 10.42.98.108:31241 | up | enabled | 0 | 4
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API-DIGIHUB | /Common/10.42.98.101:993 | available | The virtual server is available | PL_APIGW_KONG-API-DIGIHUB | 10.42.98.109:31241 | up | enabled | 0 | 4
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API-DIGIHUB | /Common/10.42.98.101:993 | available | The virtual server is available | PL_APIGW_KONG-API-DIGIHUB | 10.42.98.110:31241 | up | enabled | 0 | 4
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-API-DIGIHUB | /Common/10.42.98.101:993 | available | The virtual server is available | PL_APIGW_KONG-API-DIGIHUB | 10.42.98.119:31241 | up | enabled | 0 | 4
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS | /Common/10.42.98.98:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS | 10.42.98.102:12000 | down | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS | /Common/10.42.98.98:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS | 10.42.98.103:12000 | down | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS | /Common/10.42.98.98:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS | 10.42.98.41:12000 | down | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS | /Common/10.42.98.98:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS | 10.42.98.89:12000 | down | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS | /Common/10.42.98.98:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS | 10.42.98.91:12000 | down | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS | /Common/10.42.98.98:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS | 10.42.98.97:12000 | down | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2 | /Common/10.42.98.87:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS-CLUSTER2 | 10.42.98.102:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2 | /Common/10.42.98.87:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS-CLUSTER2 | 10.42.98.103:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2 | /Common/10.42.98.87:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS-CLUSTER2 | 10.42.98.41:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2 | /Common/10.42.98.87:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS-CLUSTER2 | 10.42.98.89:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2 | /Common/10.42.98.87:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS-CLUSTER2 | 10.42.98.91:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2 | /Common/10.42.98.87:12000 | offline | The children pool member(s) are down | PL_APIGW_KONG-REDIS-CLUSTER2 | 10.42.98.97:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2-NEW | /Common/10.49.13.38:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-CLUSTER2-NEW | 10.49.13.32:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2-NEW | /Common/10.49.13.38:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-CLUSTER2-NEW | 10.49.13.33:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2-NEW | /Common/10.49.13.38:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-CLUSTER2-NEW | 10.49.13.34:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2-NEW | /Common/10.49.13.38:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-CLUSTER2-NEW | 10.49.13.35:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2-NEW | /Common/10.49.13.38:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-CLUSTER2-NEW | 10.49.13.36:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-CLUSTER2-NEW | /Common/10.49.13.38:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-CLUSTER2-NEW | 10.49.13.37:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-NEW | /Common/10.49.13.31:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-NEW | 10.49.13.32:12000 | up | enabled | 0 | 164
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-NEW | /Common/10.49.13.31:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-NEW | 10.49.13.33:12000 | up | enabled | 0 | 164
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-NEW | /Common/10.49.13.31:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-NEW | 10.49.13.34:12000 | down | enabled | 0 | 164
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-NEW | /Common/10.49.13.31:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-NEW | 10.49.13.35:12000 | up | enabled | 0 | 164
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-NEW | /Common/10.49.13.31:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-NEW | 10.49.13.36:12000 | down | enabled | 0 | 164
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG-REDIS-NEW | /Common/10.49.13.31:12000 | available | The virtual server is available | PL_APIGW_KONG-REDIS-NEW | 10.49.13.37:12000 | up | enabled | 0 | 164
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS | /Common/10.49.13.31:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS | 10.49.13.55:12000 | up | enabled | 0 | 224
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS | /Common/10.49.13.31:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS | 10.49.13.56:12000 | up | enabled | 0 | 224
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS | /Common/10.49.13.31:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS | 10.49.13.57:12000 | down | enabled | 0 | 224
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS | /Common/10.49.13.31:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS | 10.49.13.58:12000 | up | enabled | 0 | 224
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS | /Common/10.49.13.31:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS | 10.49.13.59:12000 | down | enabled | 0 | 224
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS | /Common/10.49.13.31:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS | 10.49.13.60:12000 | up | enabled | 0 | 224
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS_CLUSTERS2 | /Common/10.49.13.38:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS_CLUSTERS2 | 10.49.13.55:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS_CLUSTERS2 | /Common/10.49.13.38:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS_CLUSTERS2 | 10.49.13.56:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS_CLUSTERS2 | /Common/10.49.13.38:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS_CLUSTERS2 | 10.49.13.57:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS_CLUSTERS2 | /Common/10.49.13.38:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS_CLUSTERS2 | 10.49.13.58:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS_CLUSTERS2 | /Common/10.49.13.38:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS_CLUSTERS2 | 10.49.13.59:12000 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_APIGW_KONG34-REDIS_CLUSTERS2 | /Common/10.49.13.38:12001 | available | The virtual server is available | PL_APIGW_KONG34-REDIS_CLUSTERS2 | 10.49.13.60:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.89:1443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.89:2443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.89:3443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.89:7443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.89:8443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.89:9443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.91:1443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.91:2443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.91:3443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.91:443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.91:7443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.91:8443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.42.98.91:9443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | 10.91.132.15:443 | up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | API_GW_DC:1443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | API_GW_DC:2443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | API_GW_DC:3443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | API_GW_DC:443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | API_GW_DC:7443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | API_GW_DC:8443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | API_GW_DC:9443 | down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | _auto_10.93.210.18:443 | up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | _auto_10.93.210.53:443 | up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443 | /Common/10.42.98.96:443 | available | The virtual server is available | API_Gateway_443 | internal-k8s-msheryszoutpost-7f1fa88fca-2108660163.ap-southeast-3.elb.amazonaws.com:443 | fqdn-up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | 10.42.98.91:1443 | down | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | 10.42.98.91:2443 | down | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | 10.91.132.15:443 | up | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | API_GW_DC:1443 | down | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | API_GW_DC:2443 | down | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | API_GW_DC:3443 | down | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | API_GW_DC:443 | down | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | API_GW_DC:7443 | down | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | API_GW_DC:8443 | down | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_API_Gateway_443_clone | /Common/10.42.98.87:443 | available | The virtual server is available | API_Gateway_443_clone | API_GW_DC:9443 | down | enabled | 0 | 8
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMAMNFT | /Common/10.42.98.96:10007 | offline | The children pool member(s) are down | CIAMAM_NFT | 10.38.34.68:10001 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMAMNFT | /Common/10.42.98.96:10007 | offline | The children pool member(s) are down | CIAMAM_NFT | 10.38.34.69:10001 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMAMNFT | /Common/10.42.98.96:10007 | offline | The children pool member(s) are down | CIAMAM_NFT | 10.38.34.70:10001 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMIDMNFT | /Common/10.42.98.96:10006 | offline | The children pool member(s) are down | CIAMIDM_NFT | 10.38.34.65:10001 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMIDMNFT | /Common/10.42.98.96:10006 | offline | The children pool member(s) are down | CIAMIDM_NFT | 10.38.34.66:10001 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMIDMNFT | /Common/10.42.98.96:10006 | offline | The children pool member(s) are down | CIAMIDM_NFT | 10.38.34.67:10001 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMIGNFT | /Common/10.42.98.96:10005 | offline | The children pool member(s) are down | CIAMIG_NFT | 10.38.10.4:10001 | user-down | enabled | 0 | 12
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMIGNFT | /Common/10.42.98.96:10005 | offline | The children pool member(s) are down | CIAMIG_NFT | 10.38.10.5:10001 | user-down | enabled | 0 | 12
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMIGNFT | /Common/10.42.98.96:10005 | offline | The children pool member(s) are down | CIAMIG_NFT | 10.38.10.6:10001 | user-down | enabled | 0 | 12
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMIGNFT | /Common/10.42.98.96:10005 | offline | The children pool member(s) are down | CIAMIG_NFT | 10.38.34.95:10001 | down | enabled | 0 | 12
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMIGNFT | /Common/10.42.98.96:10005 | offline | The children pool member(s) are down | CIAMIG_NFT | 10.38.34.96:10001 | down | enabled | 0 | 12
| esbpclbltmd1 | 10.42.96.35 | VS_CIAMIGNFT | /Common/10.42.98.96:10005 | offline | The children pool member(s) are down | CIAMIG_NFT | 10.38.34.97:10001 | down | enabled | 0 | 12
| esbpclbltmd1 | 10.42.96.35 | VS_ESB_REDIS-12000 | /Common/10.42.98.88:12000 | available | The virtual server is available | PL_ESB_REDIS-12000 | 10.42.98.26:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_ESB_REDIS-12000 | /Common/10.42.98.88:12000 | available | The virtual server is available | PL_ESB_REDIS-12000 | 10.42.98.32:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_ESB_REDIS-12000 | /Common/10.42.98.88:12000 | available | The virtual server is available | PL_ESB_REDIS-12000 | esbinfcopdapp11:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_ESB_REDIS-12000 | /Common/10.42.98.88:12000 | available | The virtual server is available | PL_ESB_REDIS-12000 | esbinfcopdapp5:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_ESB_REDIS-12001 | /Common/10.42.98.88:12001 | available | The virtual server is available | PL_ESB_REDIS-12001 | 10.42.98.26:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_ESB_REDIS-12001 | /Common/10.42.98.88:12001 | available | The virtual server is available | PL_ESB_REDIS-12001 | 10.42.98.32:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_ESB_REDIS-12001 | /Common/10.42.98.88:12001 | available | The virtual server is available | PL_ESB_REDIS-12001 | esbinfcopdapp11:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_ESB_REDIS-12001 | /Common/10.42.98.88:12001 | available | The virtual server is available | PL_ESB_REDIS-12001 | esbinfcopdapp5:12000 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp1:443 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp1:80 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp2:443 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp2:80 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp3:443 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp3:80 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp4:443 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp4:80 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp5:443 | down | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp6:443 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp7:443 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_443 | /Common/10.42.98.95:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp8:443 | up | enabled | 0 | 290
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_80 | /Common/10.42.98.95:80 | available | The children pool member(s) might be disabled | Infra_OCP | 10.42.98.88:80 | up | disabled-by-parent | 0 | 45
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_80 | /Common/10.42.98.95:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp1:80 | up | disabled-by-parent | 0 | 45
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_80 | /Common/10.42.98.95:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp2:80 | up | disabled-by-parent | 0 | 45
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_80 | /Common/10.42.98.95:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp3:80 | up | disabled-by-parent | 0 | 45
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_80 | /Common/10.42.98.95:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp4:80 | up | disabled-by-parent | 0 | 45
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_80 | /Common/10.42.98.95:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp6:80 | down | disabled-by-parent | 0 | 45
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_80 | /Common/10.42.98.95:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp7:80 | down | disabled-by-parent | 0 | 45
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_80 | /Common/10.42.98.95:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp8:80 | up | disabled-by-parent | 0 | 45
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.104:30148 | down | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.108:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.109:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.109:32671 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.110:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.110:32671 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.118:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.119:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.124:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.125:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.37:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.42.98.90:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | 10.91.131.69:443 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | _auto_10.91.130.27:443 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | _auto_10.91.133.250:443 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbactbwl2dapp2:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbactbwl3dapp1:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbactbwl3dapp2:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp10:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp1:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp2:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp3:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp4:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp8:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbinfcopdapp9:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbmsgsl3dapp1:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbmsgsl3dapp2:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbmstcopdapp4:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | esbmstcopdapp5:30148 | down | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | internal-k8s-kong34dpsznprod-f17f692a4e-88119219.ap-southeast-3.elb.amazonaws.com:443 | fqdn-up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | ocprndapp1:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | ocprndapp3:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_POC | /Common/10.42.98.101:443 | available | The virtual server is available | PL_APIGW_KONG-API | ocprndapp4:30148 | up | enabled | 44 | 59560
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp1:443 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp1:80 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp2:443 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp2:80 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp3:443 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp3:80 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp4:443 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp4:80 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp5:443 | down | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp6:443 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp7:443 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_443 | /Common/10.42.98.41:443 | available | The virtual server is available | Infra_OCP_HTTPS | esbinfcopdapp8:443 | up | enabled | 0 | 3
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_80 | /Common/10.42.98.41:80 | available | The children pool member(s) might be disabled | Infra_OCP | 10.42.98.88:80 | up | disabled-by-parent | 0 | 11
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_80 | /Common/10.42.98.41:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp1:80 | up | disabled-by-parent | 0 | 11
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_80 | /Common/10.42.98.41:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp2:80 | up | disabled-by-parent | 0 | 11
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_80 | /Common/10.42.98.41:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp3:80 | up | disabled-by-parent | 0 | 11
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_80 | /Common/10.42.98.41:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp4:80 | up | disabled-by-parent | 0 | 11
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_80 | /Common/10.42.98.41:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp6:80 | down | disabled-by-parent | 0 | 11
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_80 | /Common/10.42.98.41:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp7:80 | down | disabled-by-parent | 0 | 11
| esbpclbltmd1 | 10.42.96.35 | VS_Infra_OCP_ext_80 | /Common/10.42.98.41:80 | available | The children pool member(s) might be disabled | Infra_OCP | esbinfcopdapp8:80 | up | disabled-by-parent | 0 | 11
| esbpclbltmd1 | 10.42.96.35 | VS_Master_OCP_8443 | /Common/10.42.98.95:8443 | available | The virtual server is available | Master_OCP | esbmstcopdapp1:0 | up | enabled | 7 | 154
| esbpclbltmd1 | 10.42.96.35 | VS_Master_OCP_8443 | /Common/10.42.98.95:8443 | available | The virtual server is available | Master_OCP | esbmstcopdapp2:0 | up | enabled | 7 | 154
| esbpclbltmd1 | 10.42.96.35 | VS_Master_OCP_8443 | /Common/10.42.98.95:8443 | available | The virtual server is available | Master_OCP | esbmstcopdapp3:0 | up | enabled | 7 | 154
| esbpclbltmd1 | 10.42.96.35 | VS_Master_OCP_9000 | /Common/10.42.98.95:9000 | available | The virtual server is available | Master_OCP | esbmstcopdapp1:0 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_Master_OCP_9000 | /Common/10.42.98.95:9000 | available | The virtual server is available | Master_OCP | esbmstcopdapp2:0 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_Master_OCP_9000 | /Common/10.42.98.95:9000 | available | The virtual server is available | Master_OCP | esbmstcopdapp3:0 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623 | /Common/10.42.98.69:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpbndapp1:0 | user-down | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623 | /Common/10.42.98.69:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpbndapp1:22623 | user-down | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623 | /Common/10.42.98.69:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp1:0 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623 | /Common/10.42.98.69:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp1:22623 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623 | /Common/10.42.98.69:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp2:0 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623 | /Common/10.42.98.69:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp2:22623 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623 | /Common/10.42.98.69:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp3:0 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623 | /Common/10.42.98.69:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp3:22623 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623_INT | /Common/10.42.98.87:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpbndapp1:0 | user-down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623_INT | /Common/10.42.98.87:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpbndapp1:22623 | user-down | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623_INT | /Common/10.42.98.87:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp1:0 | up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623_INT | /Common/10.42.98.87:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp1:22623 | up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623_INT | /Common/10.42.98.87:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp2:0 | up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623_INT | /Common/10.42.98.87:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp2:22623 | up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623_INT | /Common/10.42.98.87:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp3:0 | up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_22623_INT | /Common/10.42.98.87:22623 | available | The virtual server is available | OCP4_Master_22623 | ocpmndapp3:22623 | up | enabled | 0 | 14
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443 | /Common/10.42.98.69:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpbndapp1:6443 | user-down | enabled | 4 | 267
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443 | /Common/10.42.98.69:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp1:0 | up | enabled | 4 | 267
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443 | /Common/10.42.98.69:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp1:6443 | up | enabled | 4 | 267
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443 | /Common/10.42.98.69:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp2:0 | up | enabled | 4 | 267
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443 | /Common/10.42.98.69:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp2:6443 | up | enabled | 4 | 267
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443 | /Common/10.42.98.69:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp3:0 | up | enabled | 4 | 267
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443 | /Common/10.42.98.69:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp3:6443 | up | enabled | 4 | 267
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443_INT | /Common/10.42.98.87:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpbndapp1:6443 | user-down | enabled | 152 | 1676
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443_INT | /Common/10.42.98.87:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp1:0 | up | enabled | 152 | 1676
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443_INT | /Common/10.42.98.87:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp1:6443 | up | enabled | 152 | 1676
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443_INT | /Common/10.42.98.87:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp2:0 | up | enabled | 152 | 1676
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443_INT | /Common/10.42.98.87:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp2:6443 | up | enabled | 152 | 1676
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443_INT | /Common/10.42.98.87:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp3:0 | up | enabled | 152 | 1676
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Master_6443_INT | /Common/10.42.98.87:6443 | available | The virtual server is available | OCP4_Master_6443 | ocpmndapp3:6443 | up | enabled | 152 | 1676
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_ROUTER_NBP | /Common/10.42.98.88:9443 | available | The virtual server is available | PL_OCP4_ROUTER_NBP | 10.42.98.104:31170 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_ROUTER_NBP | /Common/10.42.98.88:9443 | available | The virtual server is available | PL_OCP4_ROUTER_NBP | 10.42.98.124:31170 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_ROUTER_NBP | /Common/10.42.98.88:9443 | available | The virtual server is available | PL_OCP4_ROUTER_NBP | 10.42.98.90:31170 | up | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | 10.42.98.37:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | 10.49.13.16:32443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | 10.49.13.17:32443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | 10.49.13.18:32443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | 10.49.13.28:32443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | 10.49.13.29:32443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | 10.49.13.30:32443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | esbinfcopdapp10:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | esbinfcopdapp11:443 | down | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | esbinfcopdapp1:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | esbinfcopdapp2:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | esbinfcopdapp3:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | esbinfcopdapp8:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | esbmstcopdapp4:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | esbmstcopdapp5:443 | down | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | ocprndapp1:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | ocprndapp2:443 | down | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | ocprndapp3:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_443 | /Common/10.42.98.88:443 | available | The virtual server is available | OCP4_Router_443 | ocprndapp4:443 | up | enabled | 303 | 53623
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | 10.42.98.37:80 | up | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | esbinfcopdapp1:80 | up | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | esbinfcopdapp2:80 | up | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | esbinfcopdapp3:80 | up | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | esbinfcopdapp8:80 | up | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | esbmstcopdapp4:80 | up | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | esbmstcopdapp5:80 | down | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | ocprndapp1:80 | up | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | ocprndapp2:80 | down | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | ocprndapp3:80 | up | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_80 | /Common/10.42.98.88:80 | available | The virtual server is available | OCP4_Router_80 | ocprndapp4:80 | up | enabled | 0 | 323
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_Dcore_Migration_443 | /Common/10.42.98.69:443 | available | The virtual server is available | OCP4_Router_Dcore_Migration_443 | esbinfcopdapp1:443 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_Dcore_Migration_443 | /Common/10.42.98.69:443 | available | The virtual server is available | OCP4_Router_Dcore_Migration_443 | esbinfcopdapp2:443 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_Dcore_Migration_80 | /Common/10.42.98.69:80 | available | The virtual server is available | OCP4_Router_Dcore_Migration_80 | esbinfcopdapp1:80 | up | enabled | 0 | 74
| esbpclbltmd1 | 10.42.96.35 | VS_OCP4_Router_Dcore_Migration_80 | /Common/10.42.98.69:80 | available | The virtual server is available | OCP4_Router_Dcore_Migration_80 | esbinfcopdapp2:80 | up | enabled | 0 | 74
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.104:443 | down | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.108:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.109:443 | down | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.110:443 | down | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.118:443 | down | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.119:443 | down | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.124:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.125:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.37:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | 10.42.98.90:443 | down | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbactbwl2dapp2:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbactbwl3dapp1:443 | down | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbactbwl3dapp2:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbinfcopdapp10:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbinfcopdapp1:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbinfcopdapp2:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbinfcopdapp3:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbinfcopdapp4:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbinfcopdapp8:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbinfcopdapp9:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbmsgsl3dapp1:443 | down | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbmsgsl3dapp2:443 | down | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | esbmstcopdapp4:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | ocprndapp1:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | ocprndapp3:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OCP_Only_Router_Default_8443 | /Common/10.42.98.88:8443 | available | The virtual server is available | PL_OCP_Only_Router_Default_8443 | ocprndapp4:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_OPE_NonProd | /Common/10.42.98.95:9090 | offline | The children pool member(s) are down | OPENonProd | esbmsgsl4dapp2:9094 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OPE_NonProd | /Common/10.42.98.95:9090 | offline | The children pool member(s) are down | OPENonProd | esbmsgsl4dapp2:9095 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OPE_NonProd | /Common/10.42.98.95:9090 | offline | The children pool member(s) are down | OPENonProd | esbmsgsl4dapp2:9096 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OPE_NonProd | /Common/10.42.98.95:9090 | offline | The children pool member(s) are down | OPENonProd | esbmsgsl4dapp2:9097 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OPE_NonProd | /Common/10.42.98.95:9090 | offline | The children pool member(s) are down | OPENonProd | esbmsgsl4dapp2:9098 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OPE_NonProd | /Common/10.42.98.95:9090 | offline | The children pool member(s) are down | OPENonProd | esbmsgsl4dapp2:9099 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_OPE_NonProd | /Common/10.42.98.95:9090 | offline | The children pool member(s) are down | OPENonProd | esbmsgsl4dapp2:9100 | down | enabled | 0 | 0
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.12:31443 | down | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.13:31443 | down | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.14:31443 | down | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.16:31443 | up | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.17:31443 | up | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.18:31443 | up | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.28:31443 | up | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.29:31443 | up | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.30:31443 | up | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Ingress-default | /Common/10.49.13.20:443 | available | The virtual server is available | PL_RANCHER_RKE-Ingress-default | 10.49.13.50:31443 | down | enabled | 0 | 10379
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-KubernetesAPI | /Common/10.49.13.19:6443 | available | The virtual server is available | PL_RANCHER_RKE-KubernetesAPI | 10.49.13.6:6443 | up | enabled | 0 | 56
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-KubernetesAPI | /Common/10.49.13.19:6443 | available | The virtual server is available | PL_RANCHER_RKE-KubernetesAPI | 10.49.13.7:6443 | up | enabled | 0 | 56
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-KubernetesAPI | /Common/10.49.13.19:6443 | available | The virtual server is available | PL_RANCHER_RKE-KubernetesAPI | 10.49.13.8:6443 | up | enabled | 0 | 56
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Supervisor | /Common/10.49.13.19:9345 | available | The virtual server is available | PL_RANCHER_RKE-Supervisor | 10.49.13.10:9345 | up | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Supervisor | /Common/10.49.13.19:9345 | available | The virtual server is available | PL_RANCHER_RKE-Supervisor | 10.49.13.11:9345 | up | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Supervisor | /Common/10.49.13.19:9345 | available | The virtual server is available | PL_RANCHER_RKE-Supervisor | 10.49.13.6:9345 | up | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Supervisor | /Common/10.49.13.19:9345 | available | The virtual server is available | PL_RANCHER_RKE-Supervisor | 10.49.13.7:9345 | up | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Supervisor | /Common/10.49.13.19:9345 | available | The virtual server is available | PL_RANCHER_RKE-Supervisor | 10.49.13.8:9345 | up | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_RANCHER_RKE-Supervisor | /Common/10.49.13.19:9345 | available | The virtual server is available | PL_RANCHER_RKE-Supervisor | 10.49.13.9:9345 | up | enabled | 0 | 33
| esbpclbltmd1 | 10.42.96.35 | VS_RKE2_Ingress_ocp-nprod_7443 | /Common/10.42.98.88:7443 | available | The virtual server is available | PL_RKE2_Ingress_ocp-nprod_7443 | 10.49.13.16:32443 | up | enabled | 0 | 5863
| esbpclbltmd1 | 10.42.96.35 | VS_RKE2_Ingress_ocp-nprod_7443 | /Common/10.42.98.88:7443 | available | The virtual server is available | PL_RKE2_Ingress_ocp-nprod_7443 | 10.49.13.17:32443 | up | enabled | 0 | 5863
| esbpclbltmd1 | 10.42.96.35 | VS_RKE2_Ingress_ocp-nprod_7443 | /Common/10.42.98.88:7443 | available | The virtual server is available | PL_RKE2_Ingress_ocp-nprod_7443 | 10.49.13.18:32443 | up | enabled | 0 | 5863
| esbpclbltmd1 | 10.42.96.35 | VS_RKE2_Ingress_ocp-nprod_7443 | /Common/10.42.98.88:7443 | available | The virtual server is available | PL_RKE2_Ingress_ocp-nprod_7443 | 10.49.13.28:32443 | up | enabled | 0 | 5863
| esbpclbltmd1 | 10.42.96.35 | VS_RKE2_Ingress_ocp-nprod_7443 | /Common/10.42.98.88:7443 | available | The virtual server is available | PL_RKE2_Ingress_ocp-nprod_7443 | 10.49.13.29:32443 | up | enabled | 0 | 5863
| esbpclbltmd1 | 10.42.96.35 | VS_RKE2_Ingress_ocp-nprod_7443 | /Common/10.42.98.88:7443 | available | The virtual server is available | PL_RKE2_Ingress_ocp-nprod_7443 | 10.49.13.30:32443 | up | enabled | 0 | 5863
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_API_Servers | /Common/10.42.98.98:443 | available | The virtual server is available | Sigma_Catalog_API_Servers_4446 | pcscapismdapp1:443 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_API_Servers | /Common/10.42.98.98:443 | available | The virtual server is available | Sigma_Catalog_API_Servers_4446 | pcscapismdapp2:443 | up | enabled | 0 | 15
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_Identity_Services | /Common/10.42.98.102:443 | available | The virtual server is available | Sigma_Catalog_Identity_Services_4443 | pcscissmadapp1:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_Identity_Services | /Common/10.42.98.102:443 | available | The virtual server is available | Sigma_Catalog_Identity_Services_4443 | pcscissmpdapp1:443 | up | enabled | 0 | 22
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_Servers | /Common/10.42.98.97:443 | available | The virtual server is available | Sigma_Catalog_Servers_4445 | pcscsmadapp1:443 | up | enabled | 0 | 25
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_Servers | /Common/10.42.98.97:443 | available | The virtual server is available | Sigma_Catalog_Servers_4445 | pcscsmadapp2:443 | up | enabled | 0 | 25
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_Services | /Common/10.42.98.99:443 | available | The virtual server is available | Sigma_Catalog_Services_443 | pcscssvrdapp1:443 | down | enabled | 0 | 13
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_Services | /Common/10.42.98.99:443 | available | The virtual server is available | Sigma_Catalog_Services_443 | pcscssvrdapp2:443 | up | enabled | 0 | 13
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_Services | /Common/10.42.98.99:443 | available | The virtual server is available | Sigma_Catalog_Services_443 | pcscssvrdapp3:443 | down | enabled | 0 | 13
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Catalog_Services | /Common/10.42.98.99:443 | available | The virtual server is available | Sigma_Catalog_Services_443 | pcscssvrdapp4:443 | down | enabled | 0 | 13
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Management | /Common/10.42.98.103:443 | available | The virtual server is available | Sigma_Management_Service | 10.42.98.76:443 | up | enabled | 0 | 21
| esbpclbltmd1 | 10.42.96.35 | VS_Sigma_Management | /Common/10.42.98.103:443 | available | The virtual server is available | Sigma_Management_Service | 10.42.98.77:443 | up | enabled | 0 | 21